## Case for User
Test Case for the Seeker
Test Case Project Name : Rural Journey Created by : Created on : Re-Viewed by: Re-Viewed on: | [5 empty] | Suggestions: 1) Cost of packages and payment methods should also be added
S.No | Test Case ID | Test Case | Test Description | Pre-Condition | Test Data | Step to Execute | Expected Output | Acutal Output | Status | Remarks
1 | TES_01 | Verify that the social media link is valid | The seeker should be able to direct to social media | Seeker should be at the home page |  | 1) go to the URL -http://staging.ruraljourneys.com/# 2) scroll to the bottom 3) You will see 4 different social media icon | A seeker should be taken to a social media's account of the company | Social media link is not working or taking to any social media account | FAIL | Unchecked
2 | TES_02 | Verify that the seeker should be register successfully. | The seeker should be able to register themselves into the system. | Seeker should be at the home page | email : imnirajkharbuja@gmail.com Passowrd : pinktape@11 | 1) go to the URL -http://staging.ruraljourneys.com/# 2) At the right side of the top menu, you will see login and it's below you will see register 3)Click on the "Register" 4)Now, Register yourself with valid data | A seeker or Anyone can register themselves by putting a valid data. | The "register account" button is not working or the system is not taking any registration from a seeker. | FAIL | Unchecked
3 | TES_03 | Verify that in customized adventure's number of guests should be 0 when refreshed every time. | Application should refresh the number of guests (adults and children) numbers into 0 everytime where a seeker goes back to the search trip page. | Seeker should search for the package and be on the result page. | Destination: Dhorpatan Arrival/Departure Date: 2023/7/5 - 2023/7/10 Guest: Adult - 3 Children = 3 | 1) Go to customized adventure and put the data from test data. | When a seeker searches for a trip and goes back to the search trip page, the number of guest' type ie Adults and children should be clear or must be zero | the number of adults and children remains the same whereas the number of guests shows 0. | FAIL | Unchecked
4 | TES_04 | Verify that the seeker can search any trip they want | Random user should be able to search and filter any trip as their wishes. | Seeker should be on search page. | Destination: Pokhara Arrival/Departure Date: 2023/7/5 - 2023/7/10 Guest: Adult - 3 Children = 3 | 1) Go to customized adventure and put the data from test data. | When a seeker searches for a specific trip, it should take you to the user-searched destination. | As expecetd. | PASS | Unchecked
5 | TES_05 | Verify that the user should be registered before doing the booking | When a seeker , try to do booking without login, s/he must give his/her personal deatils | Seaker should be on search page. | From : 07/01/2023 To : 07/06/2023 Adults : 2 Children : 2 Infants : 2 | 1) go to the URL - http://staging.ruraljourneys.com/package/49/detail/ 2) Select any packages from Nepal trekking Packages 3) At BESTSELLER, put valid data from test data. | When a seeker tries to book any trip w without login s/he must give their personal information. | As expected. | PASS | Unchecked
6 | TES_06 | Verify that all drop down navigation bar shows the elements. | User should be able to view the elements in drop down list when hover at the navigation bar. | Site should be up and running. |  | 1) Hover at the "Day Trips" in navigation bar. 2) Hover at the "Featured Trips" in navigation bar. 3) Hover at the "Bhutan/Tibet" in navigation bar. | All navigation bar should show the elements in a drop down form. | Elements are not shown in drop down list in "Day Trips", "Featured Trips" and "Bhutan/Tibet". | FAIL | Unchecked
7 | TES_07 | Verify the "Show More" drop down works. | User should be able to view more elements when clicking " Show More" in categories. | User should be at all packages or packages page. |  | 1) Click at any navigation packages menu. 2) Click at " Show More" in "Categories". | "Show More" button should show more categories or work preoperly. | "Show More" button do not work. | FAIL | Unchecked
8 | TES_08 | Verify if " Submit Enquiry" button works. | User should be able to submit enquiry form. | User should be at any package booking booking page. | Your name = "Rex Lapis" Email = "lapis@gmail.com" Message = "The button does not work." | 1) Click on any package. 2) Insert the required data in "Enquiry Form" section. 3) Click on "Submit Enquiry". | Enquiry must be submitted after inserting required info. | "Submit Enquiry" does not submit the enquiry. | FAIL | Unchecked
9 | TES_09 | Verify if the user can register. | User should be able register to the website. | User should be at the landing page of Roural Journeys. | Email address= rexlapis@yopmail.com Full Name= Rex Lapis Password= RexLapis Message = "The Register account button does not work." | 1) Click on "Login" button. 2) Click on "Register". 3) Insert all the required data and click on "Register account". | User should be able to register their account. | "Register account" does not work. | FAIL | Unchecked
10

## Case for Admin
Test Case for the Admin
Test Case Project Name : Rural Journey Created by : Created on : Re-Viewed by: Re-Viewed on: | [5 empty] | Suggestion: 1)An Admin Should not be able to write or add reviews by themselves.
S.No | Test Case ID | Test Case | Test Description | Pre-Condition | Test Data | Step to Execute | Expected Output | Acutal Output | Status | Remarks
1 | TES_ADMIN_01 | Verify that the admin should be login successfully. | The admin should be able to login successfully into the system. | Admin should be at the login dashboard page | email: rural_stage_admin@gmail.com password: rural_stage_admin | 1) go to the URL -https://staging.ruraljourneys.com/dashboard/login/ | Admin should be able to login into the system successfully. | unable to login : ERROR 403 FORBIDDEN | FAIL | Unchecked
2 | TES_ADMIN_02 | Verify that the admin should be able to create or add popular places. | Admin should be able to add and create a popular places | admin should be at the admin dashboard at Popular Places list. | Place name: lil Tecca Multiple: Best of nepal Tibet | 10 go to url : https://staging.ruraljourneys.com/dashboard/popular-place/create 2) now create putting placename, image and packages and submit it. | Admin should be able to create, add, update and delete the popular places successfully. | As Expected. | PASS | Unchecked
3 | TES_ADMIN_03 | Verify that the admin can logout successfully. | Admin should be able to logout of the system successfully. | Admin should be at home page |  |  | admin should be able to logout of system succesfully | As Expected. | PASS
FAIL